## How to use
How to use this workbook
This workbook only displays status. Agents record progress in two small text files next to it
(docs/sera-sync-v3-status.csv and docs/sera-sync-v3-checks.csv) using tools/sync_v3_tracker.py.
You can keep this file open while agents work.
To see the latest status: Data → Refresh All (Ctrl+Alt+F5). It also refreshes when opened and every minute.
Don't type into the sheets: the next refresh overwrites it. To change a status, ask an agent or run the tool.
When Excel asks to save on close, either answer is fine — the status lives in the CSV files, not here.
What the agents record:
• Implementing agent: Status = In progress + Model used when it starts; Status = In review + Notes when it finishes.
• Reviewing agent (Fable 5.1 / Opus 5.5): Reviewed by.
• Committing agent: Status = Done + Commit. The tool refuses Done without a commit, or without a required review.
• The tool also refuses a model not allowed for the WP's tier, and starting a WP whose dependencies aren't Done.
What you do:
1. Pick a WP whose 'Ready?' is green (or Summary → Next ready WP).
2. Start a fresh chat with a model allowed for its tier and paste the prompt from blueprint §8.1.
3. After a phase: do the Phase Checks and record the results (tool command on that sheet, or ask an agent).
Rebuild (only when the blueprint's §3 table changes; close this file first): venv\Scripts\python tools\build_sync_v3_tracker.py — progress in the CSVs is kept.
If refresh ever shows an error about a missing file, the project folder moved: run the rebuild command.

## Work Packages
Sera Sync v3 — work packages
Grey columns come from docs/sera-sync-v3-status.csv, which agents update with tools/sync_v3_tracker.py. Data → Refresh All (Ctrl+Alt+F5) to see the latest; it also refreshes on open and every minute. Don't type into this sheet: a refresh overwrites it.
WP | Phase | What | Tier | Depends on | Dependency note | Review before merge | Recommended Claude | Gemini allowed | Status | Ready? | Unfinished deps | Model used | Model allowed? | Reviewed by | Commit | Notes | helper
P0-1 | 0 | Stop sending the whole DB after every edit | T1 |  |  | No | Claude Haiku 4.5 | Any Gemini model on the Models sheet | Done | Done | 0 | Gemini 3.1 Pro | OK | Claude Opus 5.5 | df7a850 | 2026-09-23: Re-reviewed fixes: applied timing bug fix, restored changelog
P0-2 | 0 | Fix get_sync_metrics (is_deleted → is_archived) | T1 | P0-1 | Must merge P0-1 first (see blueprint P0-2) | No | Claude Haiku 4.5 | Any Gemini model on the Models sheet | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 6d5051f | 2026-09-23: Fixed get_sync_metrics is_archived check; 799 passed, 10 pre-existing failed
P0-3 | 0 | Sender makes a consistent snapshot (sqlcipher_export) and streams it | T2 |  |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 6b38236 | 2026-09-23: make_snapshot (FileExistsError guard) + 1MB stream + prune_outgoing_snapshots, 804 passed / 10 failed
P0-4 | 0 | Receiver stages the DB and swaps it at start-up, never while running | T2 | P0-3 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 89c9aa3 | 2026-09-24: Fixed rollback WAL/SHM restoration on failed DB replace; closed RESTART_PENDING concurrency gap; 18/18 hotfix, 10/10 sync passed
P0-5 | 0 | Start-up checks that sera.key opens the DB; prompts otherwise | T2 |  |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 487d6bf | 2026-09-24: Startup password check, 3-try prompt, failure modal, salt guard, 815 passed / 10 failed. Opus 5.5 review follow-ups done (damaged-DB wording, deviations logged). Don't release before P0-6.
P0-6 | 0 | First-run "New office / Join office" + legacy join with on-screen approval | T2 | P0-3,P0-4,P0-5 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 832b053 | 2026-09-24: First-run New/Join office with on-screen modal approval, snapshot streaming, password verification, 7 new tests passed (837/10)
P0-7 | 0 | Authenticate legacy sync messages (HMAC) | T2 | P0-6 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | 89d7cfc | 2026-09-24: HMAC auth as before, plus a rollout-compatibility follow-up: rejection of a pre-P0-7 peer now carries an advisory hint (reason unchanged) and §6/§7 document the simultaneous-upgrade requirement.
P0-8 | 0 | rawPayload.db auto-heal: visible alert + audit entry | T1 |  |  | No | Claude Haiku 4.5 | Any Gemini model on the Models sheet | Done | Done | 0 | Claude Haiku 4.5 | OK | Claude Opus 5.5 | 7250dd4 | 2026-09-23: Added raw_db_was_reset tracking, audit log entry, and UI alert when auto-heal occurs. Test passes, no deviations from spec.
P0-9a | 0 | Installer firewall rules (Private + Domain + Public, v1.4) | T1 |  |  | No | Claude Haiku 4.5 | Any Gemini model on the Models sheet | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | faa61d6 | 2026-09-24: Installer firewall rules added with pre-emptive delete on upgrade and RunOnceId; test_installer_firewall_rules passed
P0-9b | 0 | In-app warning when the network profile is Public | T2 |  |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | 214a7a9 | 2026-09-24: Fixed reviewer bug #2 (PowerShell numeric NetworkCategory, verified live on Public hotspot); could not reproduce bug #1 (no enable_network_monitor flag exists in current tree); applied 4 hardening items. Full suite: 839 passed/10 failed (all pre-existing).
P0-10 | 0 | Per-adapter broadcast, "Add PC by IP", peers keyed by host | T2 |  |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 66feefe | 2026-09-24: Review fixes: 10s beacon interval (anti-flap), port 1-65535 validation, per-peer exception isolation, listener guard, rate-limited replies
P0-11 | 0 | Docs: operations-sync.md update | T1 | P0-1,P0-10 |  | No | Claude Haiku 4.5 | Any Gemini model on the Models sheet | Done | Done | 0 | Gemini 3.7 Flash | OK |  | 60667de | 2026-09-24: docs/operations-sync.md updated for Phase 0, full test suite 859 passed / 10 pre-existing failed
P1-1 | 1 | sera_keys.py: DPAPI, office.json, key id, recovery blob | T3 | P0-1,P0-2,P0-3,P0-4,P0-5,P0-6,P0-7,P0-8,P0-9a,P0-9b,P0-10,P0-11 | Phase 0 released to all PCs | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | 773eea7 | 2026-09-24: New sera_keys.py (DPAPI ctypes, Argon2id+AES-GCM wrap, office.json, key id, store/load/recover DEK) + tests/test_sera_keys.py (24); full suite 883 passed / 10 pre-existing failures
P1-2 | 1 | Start-up key resolution (office mode / legacy mode) | T2 | P1-1 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 7808f87 | 2026-09-24: Start-up key resolution (office mode DEK vs legacy PBKDF2), 889 passed / 10 pre-existing failed
P1-3 | 1 | Parsers load the key through sera_keys | T1 | P1-2 |  | No | Claude Haiku 4.5 | Any Gemini model on the Models sheet | Done | Done | 0 | Claude Sonnet 5 | OK |  | bb80c15 | 2026-09-24: Parsers try sera_keys office DEK (data dir then code dir) before legacy sera.key/salt. Full suite 891 passed / 10 pre-existing failed.
P1-4 | 1 | Migration "convert this PC to an office key" | T3 | P1-2 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | c6bcc11 | 2026-09-24: Review round 2: live-DB check refuses missing/empty file; step-6 rollback crash resumes as rollback (phase rolling_back); 28 tests; suite 936 passed / 10 pre-existing failures
P1-5 | 1 | Key-fingerprint gate everywhere | T2 | P1-2 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 1960b19 | 2026-09-24: Review fixes: zero-salt framing, legacy fetch_snapshot gated, salt backup; 937 passed / 10 failed
P1-6 | 1 | Recovery, recovery kit export, master-password change | T2 | P1-1 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 79149ab | 2026-09-24: Review blockers A and B resolved: settings backup page fixed, exact whitespace preserved with lenient fallback, full suite clean
P2-1 | 2 | Device identity + certificates | T2 | P1-1 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | 292da21 | 2026-09-24: Review-fix round 2: fixed race where load_device_identity could rename another writer's in-progress key/passphrase files; load_device_identity now read-only, cleanup moved into ensure_device_identity under the lock. Also split lock acquire-timeout from stale-steal threshold. 986 passed / 10 pre-existing failed / 2 skipped.
P2-2 | 2 | Office admin key, membership records, signatures | T3 | P2-1 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | 0820ee8 | 2026-09-24: Review fixes: revoke is final + letter/cert immutable in store_record; readers always verify; claim_admin check inside tx, refuses caller tx; 63 tests; suite 1049 passed / 10 pre-existing failed / 2 skipped
P2-3 | 2 | Mutual-TLS transport + framing | T3 | P2-1 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | 75e98e0 | 2026-09-24: Review fixes: session slots only after member check + pending-handshake caps, recv(wait=), sink/RecursionError/empty-chunk fixes; 32 transport tests; full suite 1081 passed / 10 pre-existing failures
P2-4 | 2 | Pairing with 6-digit code (SPAKE2) | T3 | P2-2,P2-3 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | d2627e2 | 2026-09-24: Review fixes: no second join in the join/close gap (close before freeing slot; close ends any session), stall warning, _install order; 38 pairing tests pass; full suite 1143 passed / 10 pre-existing failures
P2-5 | 2 | Discovery v3, address book, gossip | T2 | P2-3 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 31dc65f | 2026-09-24: Review fixes & refinements: listen=False mode, ephemeral unicast reply, sightings capping (500), open_db warning, gossip IP validation; 28 tests pass
P2-6 | 2 | Snapshot service + joiner install | T2 | P2-3,P2-4 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | e15c420 | 2026-09-24: Snapshot mTLS service, export, verification, atomic joiner install with backups (master.db last); 11 tests passed. Open items for P2-7/P2-8/P3-5 recorded in blueprint §9 P2-6 notes (P2-7 must start the snapshot server).
P2-7 | 2 | UI: Join wizard, Add workstation, Members, Remove, Hand over admin | T2 | P2-4,P2-6 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | d8af4c1 | 2026-09-25: UI: Join wizard, Add workstation, Members, Remove, Hand over/Become admin. New sync_office.py (create_new_office, join_office, AddWorkstationSession) + sync_admin.hand_over_admin. Fixed main.py office_mode start-up gap and QTimer.singleShot cross-thread bug (Qt signals) across both first-run pages. 20 new tests (test_sync_office.py, test_sync_office_ui.py) + 5 hand_over_admin tests; full suite 1279 passed / 16 pre-existing+expected failed.
P2-8 | 2 | Rejoin + salvage import for existing diverged PCs | T3 | P2-6 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | 35a9afd | 2026-09-24: New sync_rejoin.py + rejoin wizard/salvage dialog, main.py hook, Rejoin button, P2-6 sidecar abort; 35 new tests pass; full suite 1214 passed / 26 failed (10 pre-existing, 6 P3-0 expected, 10 from P2-7's unfinished dialog + its icon)
P3-0 | 3 | Multi-node test harness + convergence tests (written first) | T2 | P2-3 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | be84d98 | 2026-09-24: Review round 3 fixes: write() routes via SeraDatabase._connect for sealer hooks, dynamic time in (b), (d) conflict row on n0 only, (e) partitioned single batch & vector freeze check, stringified FK translation in digest; 7 harness passed, 6 convergence failed as expected, 1185 passed in full suite
P3-1 | 3 | Table / setting classification registry sync_schema.py | T2 |  |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | 882d054 | 2026-09-24: Round 2: client_raw_containers reverted to local (whole-row lww would have caused certain data loss via re_resolve_all_tracker_dumps' DELETE+rebuild under P3-3/P3-4 tombstone rules). New pending_creation client_container_notes TableSpec added for staff notes, lww, table itself not yet built (flagged for P3-2). 22 new schema tests + 2 database tests pass; full suite at baseline.
P3-2 | 3 | gid columns, back-fill, deterministic seed gids, _sync_* tables | T2 | P3-1 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 067828b | 2026-09-25: B1 fixed, all should-fix items addressed, fresh INI seeding harmonized; 104 passed / 0 failed
P3-3 | 3 | Capture triggers + sealer + hybrid logical clock | T3 | P3-2 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | f34baaa | 2026-09-25: Review fixes + owner option A: per-stream seq high-water mark in keys/sync_seq.json (raised after commit; unreadable file stops sealing); 86 tests pass; full suite 1366/16 (known)
P3-4 | 3 | Apply engine (field LWW, tombstones, FK translation, parking, admin signatures) | T3 | P3-3 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | 48c2335 | 2026-09-25: New sync_apply.py apply engine (LWW, tombstones incl. newer re-create for natural keys, parking, admin sigs, natural-key + PAN merge sent as merge changes) + review fixes; 58 tests pass (2 fail only with uncommitted P3-6 resequence in tree); full suite 1421/16 known
P3-5 | 3 | Sync session protocol, forwarding, poke, scheduler | T3 | P3-4,P2-5 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | 3fd8004 | 2026-09-25: New sync_engine.py (HELLO/members/CHANGES+ACK/BYE, forwarding, poke, 20s scheduler) + harness wiring; P3-0 (a)-(f) pass; 29 new tests; full suite 1467 pass / 11 pre-existing fail
P3-6 | 3 | Make start-up maintenance admin-only / id-independent (F12, F13) | T2 | P3-2 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK | Claude Opus 5.5 | 27bfc64 | 2026-09-25: Opus review fixes: gated apply resequence, hardened acceptance test; 295 sync tests pass, full suite 1432/17/3
P3-7 | 3 | Shadow mode: capture check, replica convergence, digests | T2 | P3-5 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | a897eb5 | 2026-09-25: 2026-09-25: review-fix round 1 (Opus): capture_check now replays only own-origin changes (was replaying forwarded remote copies too, failing on any PC that had received anything); enable_shadow_mode refuses when already on (silent permanent data loss). 2 new regression tests; 17 sync_shadow tests pass; full suite 1536 passed / 11 pre-existing failed / 3 skipped
P3-8 | 3 | UI refresh by table + Sera Sync panel status | T2 | P3-5 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | a897eb5 | 2026-09-25: 2026-09-25: Review fixes (Opus 5.5): use_discarded_value no longer deletes conflicts on no-op (kept for the deleted-row shape sync_apply.py actually produces, resurrection not built); wired the shadow-check timer (30min) + panel 'Run now' button that run_shadow_checks docstring asked P3-8 for; needs_update banner + stalled-streams count from peer_status()/stalled_streams(); UI refresh gated to mode live; last_ok prefers peer_status(); timer cancelled on quit; 'None' shown as '(deleted)'. 68 P3-8 tests pass; full suite 1549/11/3 (11 pre-existing).
P3-7a | 3 | Peer digest exchange for the shadow convergence check | T2 | P3-7 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | c3f91c5 | 2026-09-26: Review fixes applied (all 5 non-blocking findings from both Opus 5.5 review passes): 'vectors moved'->'vectors differ' wording; malformed digest_reply now logged as skipped instead of silently ignored; _last_local_change_at no longer stamped by a remote-driven merge (_wake_poke_sender split out); at most one digest_request answered per session (extras get busy); fixed test spy that sat on the wrong side. tests/test_sync_digest_exchange.py now 10 tests, all pass. Full suite: 1604 passed / 11 failed / 3 skipped -- the standard pre-existing set only, zero new failures.
P3-7b | 3 | Turn on shadow mode: panel action, common start point, re-enable guard | T3 | P3-7 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Done | Done | 0 | Claude Opus 5.5 | OK | Claude Opus 5.5 | c522654 | 2026-09-26: Review fixes: own changes carried over at swap (no seq gap after Reset->Start), admin Reset refused after receiving, journaled swap with crash recovery, raw required, admin identity checked; 7 new tests; full suite 1611 passed / 11 pre-existing failed / 3 skipped
P3-8a | 3 | Shadow-week readiness: parked-change age, clock-ahead warning, seal timing | T2 | P3-8 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.7 Flash | OK | Claude Opus 5.5 | 1943770 | 2026-09-26: Coalesced clock-ahead events & rate-limited log, replica parked-change age & warnings, shadow-only seal timing logger; 85 passed in sync suite
P3-8b | 3 | Panel defect fixes (Run-now gate, conflict selection, stamps, late emit) | T2 | P3-8 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Claude Sonnet 5 | OK | Claude Opus 5.5 | 1943770 (dialog fixes + 3 tests); ff87571 (remaining tests + review fixes) | 2026-09-26: Run-now gated to mode shadow, conflict selection by (db,id), stamps unified, late-emit guard; 1616 passed/11 failed(pre-existing)/3 skipped 2026-09-26: 2026-09-26: reviewed by Claude Opus 5.5, no blocking findings; 4 non-blocking findings fixed (selection-clear gap, weak sort test, timing-flaky test, UTC-vs-local flagged for owner) 2026-09-26: 2026-09-26: full suite after review fixes: 1617 passed/11 failed(pre-existing)/3 skipped
P3-9 | 3 | Go live (install converged replica, switch mode) | T2 | P3-7a,P3-7b,P3-8a,P3-8b,P3-7 | Plus: P3-7 go-live criteria met (owner decides) | Owner decision | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Not started | Ready | 0 | [5 empty] | 3
P4-1 | 4 | Remove legacy protocol, inv_frames, Rev Score, peer_logs | T2 | P3-9 | Plus: go-live done on every PC | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Not started | Waiting on 1 | 1
P4-2 | 4 | Remove sera.key/sera.salt use (keep legacy importer for restores) | T2 | P4-1 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Not started | Waiting on 1 | 1
P4-3a | 4 | Scheduled local backups (daily, keep 14) | T2 | P1-2 |  | No | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review) | Done | Done | 0 | Gemini 3.8 Flash | OK |  | 8f4d9c1
P4-3b | 4 | Restore a backup → becomes the state on every PC (D9) | T3 | P4-3a,P3-9 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Not started | Waiting on 1 | 1
P4-4 | 4 | Change-log compaction | T3 | P3-9 |  | Yes – Fable 5.1 / Opus 5.5 | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision) | Not started | Waiting on 1 | 1
P4-5 | 4 | Docs + test clean-up | T1 | P4-1,P4-2,P4-3a,P4-3b,P4-4 |  | No | Claude Haiku 4.5 | Any Gemini model on the Models sheet | Not started | Waiting on 4 | 4
Note on E4: WP ids separated by commas. 'Unfinished deps' counts those not yet Done.

## Summary
Progress summary
Phase | Name | WPs | Done | In progress / review | Blocked | % done | Next ready WP
0 | Hotfix (2.x) | 12 | 12 | 0 | 0 | 100% | none
1 | Office key (3.0) | 6 | 6 | 0 | 0 | 100% | none
2 | Devices & pairing (3.0) | 8 | 8 | 0 | 0 | 100% | none
3 | Change replication (3.1 shadow / 3.2 live) | 14 | 13 | 0 | 0 | 92.86% | P3-9
4 | Cleanup (3.3) | 6 | 1 | 0 | 0 | 16.67% | none
| Total | 46 | 40 | 0 | 0 | 86.96%
By tier
Tier | Meaning | WPs | Done | Need review
T1 | Mechanical | 7 | 6 | 0
T2 | Standard | 27 | 24 | 12
T3 | Expert | 12 | 10 | 12
Latest status update in the CSV: |  |  | 2026-09-26 15:28

## Phase Checks
Hands-on checks before releasing each phase (blueprint §8.4)
Record results with: venv\Scripts\python tools\sync_v3_tracker.py check <#> --result Pass (or ask an agent). Grey columns come from docs/sera-sync-v3-checks.csv.
# | Phase | Check | Related WP | Result | Date | Notes
1 | 0 | Installer adds the firewall rule: netsh advfirewall firewall show rule name="Amas Sera Sync" | P0-9a | Pass | 2026-09-26 | Reported by owner 2026-09-26
2 | 0 | Sera Sync panel warns when the PC's network is set to Public | P0-9b | Pass | 2026-09-26 | Reported by owner 2026-09-26
3 | 0 | Spare PC: first run → Join office → approve on the other PC → enter office password → app opens | P0-6 | Not run
4 | 0 | Manual push from the dialog lands only after the receiving PC restarts, and the DB opens | P0-4 | Not run
5 | 0 | A Wi-Fi PC and a wired PC see each other after Add PC by IP | P0-10 | Not run
6 | 0 | Editing a client no longer triggers 'Live update synced' toasts on other PCs | P0-1 | Not run
7 | 1 | Admin PC: Convert to office key succeeds; app opens without a password prompt | P1-4 | Pass | 2026-09-26
8 | 1 | Recovery kit exported to USB and stored safely | P1-6 | Pass | 2026-09-26
9 | 1 | Log into a second Windows account on the admin PC → recovery dialog → master password unlocks | P1-6 | Not run
10 | 1 | DOM Parser and SDC Parser still run on the converted PC | P1-3 | Not run
11 | 2 | Add workstation → code → Join office on another PC works end to end | P2-4, P2-6 | Not run
12 | 2 | Wrong code 3 times closes the pairing window | P2-4 | Not run
13 | 2 | Removed PC can no longer sync (panel shows it as removed) | P2-7 | Not run
14 | 2 | Become admin with the master password on a second PC; the old admin PC shows it is no longer admin | P2-2 | Not run
15 | 2 | Every legacy PC: Rejoin → salvage dry run reviewed → import; salvage report saved | P2-8 | Not run
16 | 3 | Shadow mode on all PCs for 7 days; zero capture mismatches; replica digests converge | P3-7 | Not run
17 | 3 | Two people edit different fields of the same client on two PCs → both edits appear everywhere | P3-4 | Not run
18 | 3 | Set one PC's clock 2 hours ahead → panel shows the clock warning; set it back | P3-3 | Not run
19 | 3 | On a non-admin PC, enter admin mode and change a setting → it appears on every PC | P3-4 | Not run
20 | 3 | On a non-admin PC, try to edit the staff list → told to use the admin PC or Become admin | P3-1 | Not run
21 | 3 | Go-live restart on every PC; clients count matches on all PCs | P3-9 | Not run
22 | 4 | An old 2.x install can no longer push to the office | P4-1 | Not run
23 | 4 | A daily backup folder appears in backups/ | P4-3a | Not run
24 | 4 | Restore dry run shows sensible counts (cancel at the RESTORE prompt unless you mean it) | P4-3b | Not run

## Models
Model × tier matrix
Yes = allowed. Caution = allowed only if a Fable 5.1 / Opus 5.5 session reviews the diff before merge. No = don't use for that tier. Gemini is never used for T3 (owner decision 2026-09-23).
Model | Provider | Model ID | Status | T1 | T2 | T3 | Can review T3 work | Notes
Claude Fable 5.1 | Anthropic | claude-fable-5-1 | GA (Sep 2026) | Yes | Yes | Yes | Yes | Most capable Claude model. First choice for T3 work and all reviews.
Claude Opus 5.5 | Anthropic | claude-opus-5-5 | GA | Yes | Yes | Yes | Yes | T3-capable. Alternative to Fable for T3 work and reviews.
Claude Sonnet 5 | Anthropic | claude-sonnet-5 | GA | Yes | Yes | No | No | Default for T2.
Claude Haiku 4.5 | Anthropic | claude-haiku-4-5-20251001 | GA | Yes | No | No | No | Default for T1.
Gemini 3.8 Flash | Google | gemini-3.8-flash | Stable (GA 2026-09-02) | Yes | Yes | No | No | Best Gemini choice for T2 (Google: long-horizon software engineering, agents).
Gemini 3.1 Pro | Google | gemini-3.1-pro-preview | Preview | Yes | Yes | No | No | Strong reasoning; preview model, so behaviour can change between sessions.
Gemini 3.7 Flash | Google | gemini-3.7-flash | Stable | Yes | Yes | No | No | Previous-generation Flash for complex coding; fine for T2.
Gemini 3.6 Flash | Google | gemini-3.6-flash | Stable | Yes | Caution | No | No | T2 only with a Fable/Opus review of the diff.
Gemini 3 Flash | Google | gemini-3-flash-preview | Preview | Yes | Caution | No | No | Older preview; T2 only with a Fable/Opus review of the diff.
Gemini 2.5 Pro | Google | gemini-2.5-pro | Legacy (access-limited) | Yes | Caution | No | No | Only if your account still has access; T2 only with review.
Gemini 3.5 Flash | Google | gemini-3.5-flash | Stable (legacy) | Yes | No | No | No | Baseline model; T1 only.
Gemini 3.5 Flash-Lite | Google | gemini-3.5-flash-lite | Stable | Yes | No | No | No | Fast/cheap; T1 only.
Gemini 3.1 Flash-Lite | Google | gemini-3.1-flash-lite | Stable | Yes | No | No | No | Fast/cheap; T1 only.
Gemini 2.5 Flash | Google | gemini-2.5-flash | Legacy (access-limited) | Yes | No | No | No | T1 only.
Gemini 2.5 Flash-Lite | Google | gemini-2.5-flash-lite | Legacy (access-limited) | Yes | No | No | No | T1 only.
Sources
Gemini list: Google AI for Developers, 'Models ¦ Gemini API', https://ai.google.dev/gemini-api/docs/models (fetched 2026-09-23). Claude list: Claude Code model list + Anthropic's Fable 5.1 announcement. Tier permissions are Claude's recommendation for this project, not vendor ratings.
Tier defaults
Tier | Meaning | Recommended Claude | Gemini allowed
T1 | Mechanical | Claude Haiku 4.5 | Any Gemini model on the Models sheet
T2 | Standard | Claude Sonnet 5 | Gemini 3.8 Flash, 3.1 Pro, 3.7 Flash (3.6 Flash / 3 Flash / 2.5 Pro only with review)
T3 | Expert | Claude Fable 5.1 or Opus 5.5 | Not allowed (owner decision)

## StatusData (hidden)
WP | Status | Model used | Reviewed by | Commit | Notes | Updated
P0-1 | Done | Gemini 3.1 Pro | Claude Opus 5.5 | df7a850 | 2026-09-23: Re-reviewed fixes: applied timing bug fix, restored changelog
P0-2 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 6d5051f | 2026-09-23: Fixed get_sync_metrics is_archived check; 799 passed, 10 pre-existing failed
P0-3 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 6b38236 | 2026-09-23: make_snapshot (FileExistsError guard) + 1MB stream + prune_outgoing_snapshots, 804 passed / 10 failed
P0-4 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 89c9aa3 | 2026-09-24: Fixed rollback WAL/SHM restoration on failed DB replace; closed RESTART_PENDING concurrency gap; 18/18 hotfix, 10/10 sync passed
P0-5 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 487d6bf | 2026-09-24: Startup password check, 3-try prompt, failure modal, salt guard, 815 passed / 10 failed. Opus 5.5 review follow-ups done (damaged-DB wording, deviations logged). Don't release before P0-6.
P0-6 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 832b053 | 2026-09-24: First-run New/Join office with on-screen modal approval, snapshot streaming, password verification, 7 new tests passed (837/10)
P0-7 | Done | Claude Sonnet 5 | Claude Opus 5.5 | 89d7cfc | 2026-09-24: HMAC auth as before, plus a rollout-compatibility follow-up: rejection of a pre-P0-7 peer now carries an advisory hint (reason unchanged) and §6/§7 document the simultaneous-upgrade requirement.
P0-8 | Done | Claude Haiku 4.5 | Claude Opus 5.5 | 7250dd4 | 2026-09-23: Added raw_db_was_reset tracking, audit log entry, and UI alert when auto-heal occurs. Test passes, no deviations from spec.
P0-9a | Done | Gemini 3.8 Flash | Claude Opus 5.5 | faa61d6 | 2026-09-24: Installer firewall rules added with pre-emptive delete on upgrade and RunOnceId; test_installer_firewall_rules passed
P0-9b | Done | Claude Sonnet 5 | Claude Opus 5.5 | 214a7a9 | 2026-09-24: Fixed reviewer bug #2 (PowerShell numeric NetworkCategory, verified live on Public hotspot); could not reproduce bug #1 (no enable_network_monitor flag exists in current tree); applied 4 hardening items. Full suite: 839 passed/10 failed (all pre-existing).
P0-10 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 66feefe | 2026-09-24: Review fixes: 10s beacon interval (anti-flap), port 1-65535 validation, per-peer exception isolation, listener guard, rate-limited replies
P0-11 | Done | Gemini 3.7 Flash |  | 60667de | 2026-09-24: docs/operations-sync.md updated for Phase 0, full test suite 859 passed / 10 pre-existing failed
P1-1 | Done | Claude Opus 5.5 | Claude Opus 5.5 | 773eea7 | 2026-09-24: New sera_keys.py (DPAPI ctypes, Argon2id+AES-GCM wrap, office.json, key id, store/load/recover DEK) + tests/test_sera_keys.py (24); full suite 883 passed / 10 pre-existing failures
P1-2 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 7808f87 | 2026-09-24: Start-up key resolution (office mode DEK vs legacy PBKDF2), 889 passed / 10 pre-existing failed
P1-3 | Done | Claude Sonnet 5 |  | bb80c15 | 2026-09-24: Parsers try sera_keys office DEK (data dir then code dir) before legacy sera.key/salt. Full suite 891 passed / 10 pre-existing failed.
P1-4 | Done | Claude Opus 5.5 | Claude Opus 5.5 | c6bcc11 | 2026-09-24: Review round 2: live-DB check refuses missing/empty file; step-6 rollback crash resumes as rollback (phase rolling_back); 28 tests; suite 936 passed / 10 pre-existing failures | 2026-09-24 14:39
P1-5 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 1960b19 | 2026-09-24: Review fixes: zero-salt framing, legacy fetch_snapshot gated, salt backup; 937 passed / 10 failed | 2026-09-24 14:46
P1-6 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 79149ab | 2026-09-24: Review blockers A and B resolved: settings backup page fixed, exact whitespace preserved with lenient fallback, full suite clean | 2026-09-24 16:49
P2-1 | Done | Claude Sonnet 5 | Claude Opus 5.5 | 292da21 | 2026-09-24: Review-fix round 2: fixed race where load_device_identity could rename another writer's in-progress key/passphrase files; load_device_identity now read-only, cleanup moved into ensure_device_identity under the lock. Also split lock acquire-timeout from stale-steal threshold. 986 passed / 10 pre-existing failed / 2 skipped. | 2026-09-24 17:07
P2-2 | Done | Claude Opus 5.5 | Claude Opus 5.5 | 0820ee8 | 2026-09-24: Review fixes: revoke is final + letter/cert immutable in store_record; readers always verify; claim_admin check inside tx, refuses caller tx; 63 tests; suite 1049 passed / 10 pre-existing failed / 2 skipped | 2026-09-24 17:54
P2-3 | Done | Claude Opus 5.5 | Claude Opus 5.5 | 75e98e0 | 2026-09-24: Review fixes: session slots only after member check + pending-handshake caps, recv(wait=), sink/RecursionError/empty-chunk fixes; 32 transport tests; full suite 1081 passed / 10 pre-existing failures | 2026-09-24 18:14
P2-4 | Done | Claude Opus 5.5 | Claude Opus 5.5 | d2627e2 | 2026-09-24: Review fixes: no second join in the join/close gap (close before freeing slot; close ends any session), stall warning, _install order; 38 pairing tests pass; full suite 1143 passed / 10 pre-existing failures | 2026-09-24 18:59
P2-5 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 31dc65f | 2026-09-24: Review fixes & refinements: listen=False mode, ephemeral unicast reply, sightings capping (500), open_db warning, gossip IP validation; 28 tests pass | 2026-09-24 19:16
P2-6 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | e15c420 | 2026-09-24: Snapshot mTLS service, export, verification, atomic joiner install with backups (master.db last); 11 tests passed. Open items for P2-7/P2-8/P3-5 recorded in blueprint §9 P2-6 notes (P2-7 must start the snapshot server). | 2026-09-24 21:47
P2-7 | Done | Claude Sonnet 5 | Claude Opus 5.5 | d8af4c1 | 2026-09-25: UI: Join wizard, Add workstation, Members, Remove, Hand over/Become admin. New sync_office.py (create_new_office, join_office, AddWorkstationSession) + sync_admin.hand_over_admin. Fixed main.py office_mode start-up gap and QTimer.singleShot cross-thread bug (Qt signals) across both first-run pages. 20 new tests (test_sync_office.py, test_sync_office_ui.py) + 5 hand_over_admin tests; full suite 1279 passed / 16 pre-existing+expected failed. | 2026-09-25 00:47
P2-8 | Done | Claude Opus 5.5 | Claude Opus 5.5 | 35a9afd | 2026-09-24: New sync_rejoin.py + rejoin wizard/salvage dialog, main.py hook, Rejoin button, P2-6 sidecar abort; 35 new tests pass; full suite 1214 passed / 26 failed (10 pre-existing, 6 P3-0 expected, 10 from P2-7's unfinished dialog + its icon) | 2026-09-25 00:03
P3-0 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | be84d98 | 2026-09-24: Review round 3 fixes: write() routes via SeraDatabase._connect for sealer hooks, dynamic time in (b), (d) conflict row on n0 only, (e) partitioned single batch & vector freeze check, stringified FK translation in digest; 7 harness passed, 6 convergence failed as expected, 1185 passed in full suite | 2026-09-24 21:50
P3-1 | Done | Claude Sonnet 5 | Claude Opus 5.5 | 882d054 | 2026-09-24: Round 2: client_raw_containers reverted to local (whole-row lww would have caused certain data loss via re_resolve_all_tracker_dumps' DELETE+rebuild under P3-3/P3-4 tombstone rules). New pending_creation client_container_notes TableSpec added for staff notes, lww, table itself not yet built (flagged for P3-2). 22 new schema tests + 2 database tests pass; full suite at baseline. | 2026-09-24 21:37
P3-2 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 067828b | 2026-09-25: B1 fixed, all should-fix items addressed, fresh INI seeding harmonized; 104 passed / 0 failed | 2026-09-25 00:53
P3-3 | Done | Claude Opus 5.5 | Claude Opus 5.5 | f34baaa | 2026-09-25: Review fixes + owner option A: per-stream seq high-water mark in keys/sync_seq.json (raised after commit; unreadable file stops sealing); 86 tests pass; full suite 1366/16 (known) | 2026-09-25 02:12
P3-4 | Done | Claude Opus 5.5 | Claude Opus 5.5 | 48c2335 | 2026-09-25: New sync_apply.py apply engine (LWW, tombstones incl. newer re-create for natural keys, parking, admin sigs, natural-key + PAN merge sent as merge changes) + review fixes; 58 tests pass (2 fail only with uncommitted P3-6 resequence in tree); full suite 1421/16 known | 2026-09-25 15:22
P3-5 | Done | Claude Opus 5.5 | Claude Opus 5.5 | 3fd8004 | 2026-09-25: New sync_engine.py (HELLO/members/CHANGES+ACK/BYE, forwarding, poke, 20s scheduler) + harness wiring; P3-0 (a)-(f) pass; 29 new tests; full suite 1467 pass / 11 pre-existing fail | 2026-09-25 17:46
P3-6 | Done | Gemini 3.8 Flash | Claude Opus 5.5 | 27bfc64 | 2026-09-25: Opus review fixes: gated apply resequence, hardened acceptance test; 295 sync tests pass, full suite 1432/17/3 | 2026-09-25 16:16
P3-7 | Done | Claude Sonnet 5 | Claude Opus 5.5 | a897eb5 | 2026-09-25: 2026-09-25: review-fix round 1 (Opus): capture_check now replays only own-origin changes (was replaying forwarded remote copies too, failing on any PC that had received anything); enable_shadow_mode refuses when already on (silent permanent data loss). 2 new regression tests; 17 sync_shadow tests pass; full suite 1536 passed / 11 pre-existing failed / 3 skipped | 2026-09-25 19:32
P3-8 | Done | Claude Sonnet 5 | Claude Opus 5.5 | a897eb5 | 2026-09-25: 2026-09-25: Review fixes (Opus 5.5): use_discarded_value no longer deletes conflicts on no-op (kept for the deleted-row shape sync_apply.py actually produces, resurrection not built); wired the shadow-check timer (30min) + panel 'Run now' button that run_shadow_checks docstring asked P3-8 for; needs_update banner + stalled-streams count from peer_status()/stalled_streams(); UI refresh gated to mode live; last_ok prefers peer_status(); timer cancelled on quit; 'None' shown as '(deleted)'. 68 P3-8 tests pass; full suite 1549/11/3 (11 pre-existing). | 2026-09-25 19:32
P3-7a | Done | Claude Sonnet 5 | Claude Opus 5.5 | c3f91c5 | 2026-09-26: Review fixes applied (all 5 non-blocking findings from both Opus 5.5 review passes): 'vectors moved'->'vectors differ' wording; malformed digest_reply now logged as skipped instead of silently ignored; _last_local_change_at no longer stamped by a remote-driven merge (_wake_poke_sender split out); at most one digest_request answered per session (extras get busy); fixed test spy that sat on the wrong side. tests/test_sync_digest_exchange.py now 10 tests, all pass. Full suite: 1604 passed / 11 failed / 3 skipped -- the standard pre-existing set only, zero new failures. | 2026-09-26 09:33
P3-7b | Done | Claude Opus 5.5 | Claude Opus 5.5 | c522654 | 2026-09-26: Review fixes: own changes carried over at swap (no seq gap after Reset->Start), admin Reset refused after receiving, journaled swap with crash recovery, raw required, admin identity checked; 7 new tests; full suite 1611 passed / 11 pre-existing failed / 3 skipped | 2026-09-26 10:02
P3-8a | Done | Gemini 3.7 Flash | Claude Opus 5.5 | 1943770 | 2026-09-26: Coalesced clock-ahead events & rate-limited log, replica parked-change age & warnings, shadow-only seal timing logger; 85 passed in sync suite | 2026-09-26 15:27
P3-8b | Done | Claude Sonnet 5 | Claude Opus 5.5 | 1943770 (dialog fixes + 3 tests); ff87571 (remaining tests + review fixes) | 2026-09-26: Run-now gated to mode shadow, conflict selection by (db,id), stamps unified, late-emit guard; 1616 passed/11 failed(pre-existing)/3 skipped 2026-09-26: 2026-09-26: reviewed by Claude Opus 5.5, no blocking findings; 4 non-blocking findings fixed (selection-clear gap, weak sort test, timing-flaky test, UTC-vs-local flagged for owner) 2026-09-26: 2026-09-26: full suite after review fixes: 1617 passed/11 failed(pre-existing)/3 skipped | 2026-09-26 15:28
P3-9 | Not started
P4-1 | Not started
P4-2 | Not started
P4-3a | Done | Gemini 3.8 Flash |  | 8f4d9c1 |  | 2026-09-25 18:13
P4-3b | Not started
P4-4 | Not started
P4-5 | Not started

## ChecksData (hidden)
Check | Result | Date | Notes
1 | Pass | 2026-09-26 | Reported by owner 2026-09-26
2 | Pass | 2026-09-26 | Reported by owner 2026-09-26
3 | Not run
4 | Not run
5 | Not run
6 | Not run
7 | Pass | 2026-09-26
8 | Pass | 2026-09-26
9 | Not run
10 | Not run
11 | Not run
12 | Not run
13 | Not run
14 | Not run
15 | Not run
16 | Not run
17 | Not run
18 | Not run
19 | Not run
20 | Not run
21 | Not run
22 | Not run
23 | Not run
24 | Not run